## Overview
TF Diff Explainer — Development Tracker
Chrome Extension · 11-week build plan · 4 phases
Phase | Timeline | Effort | Tasks | Progress | Deliverable
Phase 1 — Foundation | Weeks 1–2 | ~20 hrs | 16 | 0% | Loadable extension that detects GitHub/GitLab PR pages with .tf diffs and renders a sidebar shell
Phase 2 — Core engine | Weeks 3–5 | ~35 hrs | 16 | 0% | Fully functional local classifier — sidebar shows risk level, per-finding details, and dependency minimap with no API call required
Phase 3 — AI layer | Weeks 6–8 | ~30 hrs | 15 | 0% | Full sidebar with local risk + AI summary + PR description copy + rollback checklist, all rendering progressively
Phase 4 — Polish + ship | Weeks 9–11 | ~25 hrs | 16 | 0% | Published Chrome extension with org policy support, onboarding, and full documentation — ready for team distribution

## Phase 1
Phase 1 — Foundation
Weeks 1–2 · ~20 hrs · Deliverable: Loadable extension that detects GitHub/GitLab PR pages with .tf diffs and renders a sidebar shell
Task group | Task | Owner | Start date | Status | Notes
Project scaffold | Init repo with manifest v3 skeleton | Dev |  | Not started
| Configure ESLint + Prettier | Dev |  | Not started
| Set up hot-reload dev workflow via web-ext | Dev |  | Not started
| Add GitHub Actions CI for lint + build | Dev/CI |  | Not started
Page detection | URL matcher for GitHub PR pages | Dev |  | Not started
| URL matcher for GitLab MR pages | Dev |  | Not started
| MutationObserver for SPA navigation | Dev |  | Not started
| Detect presence of .tf files in diff | Dev |  | Not started
Settings popup | Popup HTML with API key input | Dev/UX |  | Not started
| Store key in chrome.storage.local | Dev |  | Not started
| Validate key format on save | Dev |  | Not started
| Toggle extension on/off per-site | Dev |  | Not started
Sidebar shell | Inject sidebar div into PR page DOM | Dev |  | Not started
| CSS positioning alongside PR timeline | Dev/UX |  | Not started
| Skeleton loading state | Dev/UX |  | Not started
| Collapse/expand toggle | Dev/UX |  | Not started
Status legend | Not started | In progress | Done | Blocked

## Phase 2
Phase 2 — Core engine
Weeks 3–5 · ~35 hrs · Deliverable: Fully functional local classifier — sidebar shows risk level, per-finding details, and dependency minimap with no API call required
Task group | Task | Owner | Start date | Status | Notes
Diff extraction | Parse GitHub diff DOM for .tf files | Dev |  | Not started
| Parse GitLab diff DOM (different selectors) | Dev |  | Not started
| Extract added/removed lines per file | Dev |  | Not started
| Identify resource type from HCL lines | Dev |  | Not started
Risk classifier | Rule engine: regex patterns per resource type | Dev |  | Not started
| High/medium/low scoring logic | Dev |  | Not started
| Classify: SG, route tables, VPC, subnets, IAM | Dev |  | Not started
| Unit tests for each rule | Dev/Test |  | Not started
Dependency map | Parse HCL resource references in diff | Dev |  | Not started
| Build adjacency list of changed → affected resources | Dev |  | Not started
| Render minimap as inline SVG | Dev/UX |  | Not started
| Click node to highlight in diff | Dev/UX |  | Not started
Sidebar UI | Risk badge + colour coding | Dev/UX |  | Not started
| Per-finding rows with severity dots | Dev/UX |  | Not started
| Affected resource chips | Dev/UX |  | Not started
| Dark mode support | Dev/UX |  | Not started
Status legend | Not started | In progress | Done | Blocked

## Phase 3
Phase 3 — AI layer
Weeks 6–8 · ~30 hrs · Deliverable: Full sidebar with local risk + AI summary + PR description copy + rollback checklist, all rendering progressively
Task group | Task | Owner | Start date | Status | Notes
Claude integration | Fetch wrapper to api.anthropic.com from content script | Dev |  | Not started
| Prompt template: diff + risk findings → summary | Dev |  | Not started
| Streaming response rendering | Dev |  | Not started
| Error states: rate limit, auth failure, timeout | Dev |  | Not started
PR description gen | Prompt: produce formatted PR description block | Dev |  | Not started
| "Copy to PR" button with clipboard API | Dev/UX |  | Not started
| Optional: post comment via GitHub API | Dev |  | Not started
| Template customisation in settings | Dev/UX |  | Not started
Rollback advisor | Prompt: generate ordered rollback steps from diff | Dev |  | Not started
| Render as numbered checklist in sidebar | Dev/UX |  | Not started
| One-click copy to clipboard | Dev/UX |  | Not started
Performance | Cache API response per PR + diff hash | Dev |  | Not started
| Debounce re-analysis on diff re-render | Dev |  | Not started
| Show local classifier result instantly, AI async | Dev |  | Not started
| Token budget: keep prompt under 2k tokens | Dev |  | Not started
Status legend | Not started | In progress | Done | Blocked

## Phase 4
Phase 4 — Polish + ship
Weeks 9–11 · ~25 hrs · Deliverable: Published Chrome extension with org policy support, onboarding, and full documentation — ready for team distribution
Task group | Task | Owner | Start date | Status | Notes
Policy engine | Load org policy YAML from settings or URL | Dev |  | Not started
| Extend risk classifier with custom rules | Dev |  | Not started
| Flag org-specific violations (e.g. banned CIDRs) | Dev |  | Not started
| Share policy file across team via gist/repo | Dev/Ops |  | Not started
Build pipeline | Vite/esbuild bundle for content + background scripts | Dev/CI |  | Not started
| Minify + source maps for prod | Dev/CI |  | Not started
| Automated zip packaging for Chrome Web Store | Dev/CI |  | Not started
| Version bump + changelog automation | Dev/CI |  | Not started
UX polish | Onboarding flow for first install | Dev/UX |  | Not started
| Keyboard shortcut to toggle sidebar | Dev/UX |  | Not started
| Feedback button (thumbs up/down per analysis) | Dev/UX |  | Not started
| Accessibility audit (focus management, ARIA) | Dev/UX |  | Not started
Docs + privacy | README: install, configure, usage | Docs |  | Not started
| Privacy policy (required for Chrome Web Store) | Docs |  | Not started
| CONTRIBUTING guide | Docs |  | Not started
| Architecture decision records (ADRs) | Docs |  | Not started
Status legend | Not started | In progress | Done | Blocked